INV project. June –November 2014. Dead lines

| What? | When? | Who does it? Who is responsible for? |
| --- | --- | --- |
| Testing |  |  |
| End of observation period | 30 June | All partners will send to IFI self observation protocols describing the situation until the 30th of June, by the 11th of July |
| Design and distribution of a new protocol | 1 July – 30 August | Proposal by FCSD. Coordination by IFI. Consultancy by AIPD. |
| Testing of the new protocol | 1 – 30 September | All available partners with their professionals (1 or two observation protocols each). |
| II national training | 10 October (In fact, it will be organised in two days, one of them will be the 10th, in order to hold a teleconference). | All partners. Ifi responsible for coordination. |
| Sending the idea of the video | 18 June | All partners to FCSD, responsible. |
| Producing the video in the original language and sending to the other partners | End of July | All partners |
| Subtitling the video in the other languages | Half September | Alll partners |
| Uploading 4 videos with subtitles | 30 September | All partners, Down Alapitvany responsible for coordination |
| Dissemination |  |  |
| English version of the leaflet to partners | 12th-16th June | FCSD |
| Translation of the leaflet | 23 June | All partners |
| Sending of the leaflet | Before the end of June and II sending november | All partners. Down Alapitvany responsible for coordination and reporting. |
| Exploitation plan (universities, decision makers, similar institutions) | 30 June | All partners will present a dissemination plan to AIPD as far as their own countries are concerned. |
| Last coordination meeting | 11-12 december | AIPD |
| Evaluation | 10th of July | All national trainers send to Monica Berarducci the observation forms (time t1 being the 30th of June) |