|  |  | I year |  |  |  |  |  |  |  |  |  |  |  | II year |  |  |  |  |  |  |  |  |  |  |  | III year |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |
|  |  | 1 O | 2 N | 3 D | 4 J | 5 F | 6 M | 7 A | 8 M | 9 J | 10 J | 11 A | 12 S | 13 O | 14 N | 15 D | 16 J | 17 F | 18 M | 19 A | 20 M | 21 J | 22 J | 23 A | 24 S | 25 O | 26 N | 27 D | 28 J |
| WP 1 P1 | MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Set up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | I coord meeting (Barcelona) |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Report I coord meeting P3 |  | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | II coord meeting (Madrid?) |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Report II coord meeting P3 |  |  |  |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Midterm report EACEA (P1) |  |  |  |  |  |  |  |  |  |  |  |  | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | III coord meeting (Budapest?) |  |  |  |  |  |  |  |  |  |  |  |  |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Report II coord meeting P3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | VI coord meeting (?) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5 |  |  |  |  |  |  |  |
|  | Report IV coord meeting P3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25 |  |  |  |  |  |  |  |
|  | Final coord meeting (Roma) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 16 |  |  |  |  |
|  | Final coord meeting report P3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 31 |  |  |  |  |
|  | Final report EACEA (P1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Marz 2015 |
| WP 2 | Preparation of resources and tools for Focus Groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Questions grid |  |  | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Observation grid |  |  |  | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Guidelines |  |  |  | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP 3 P4 | INV Focus Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | National Focus Groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Report on National Focus Groups |  |  |  |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final report “Define the Essential” |  |  |  |  |  |  |  | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4 P1 | Pedagogical Model INV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Researcher/trainers meeting on Pedag. Model |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Meeting report |  |  |  |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Pedagogical Model handbook |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |
| WP 5 P1 | INV Training Path |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training of trainers |  |  |  |  |  |  |  |  |  |  |  |  |  | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training Path handbook |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |
| WP 6 P2 | Training Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | National workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | On-line workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training testing evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Training Workshop report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 23 |  |  |  |  |
|  | CD ROM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 23 |  |  |  |  |
| WP 7 P2 | Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Planning |  |  |  |  |  |  |  | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | INV Midterm report |  |  |  |  |  |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | INV Final report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 |
| WP 8 P3 | Dissemination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Planning |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Web site |  |  |  | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Thematic Workshop |  |  |  |  |  |  |  |  |  |  |  |  | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Workshop report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP 9 | Exploitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Public event |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30 |  |  |  |
|  |  | 1 O | 2 N | 3 D | 4 J | 5 F | 6 M | 7 A | 8 M | 9 J | 10 J | 11 A | 12 S | 13 O | 14 N | 15 D | 16 J | 17 F | 18 M | 19 A | 20 M | 21 J | 22 J | 23 A | 24 S | 25 O | 26 N | 27 D | 28 J |
|  |  | 2012 |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |  |  |  |  |  |  |  | 2015 |