“L’essenziale è invisibile agli occhi – INV” , Grundtvig project

Minutes of the first co-ordination meeting , held in Barcelona, Fundaciò Catalana Sindrome de Down.

November 15-17 , 2012

Attendants

FCSD: Marius Peralta, Ramon Coma, Cristina Herreros

AIPD: Paola Vulterini, Maria Giulia Senni, Giorgia Scivola,

Down Foundation HU: Katalin Gruiz,

IFI: Alicia García-Madrid Colado,

November, 15, pm

| Topic | Speaker | Attach | Comments |
| --- | --- | --- | --- |
| Presentation of each partner | Marius Peralta, Giorgia Scivola, Katalin Gruiz, Alicia García-Madrid Colado | 1,2,3,4 |  |
| Self introduction of participants |  |  |  |
| Presentation of the project | Paola Vulterini | 5 | *Should we define the concept of PERSON WITH Down syndrome and severe problems or not? |

November, 16

| Topic | Speaker | Attach | Comments |
| --- | --- | --- | --- |
| Visit of the FCSD | FCSD staff |  |  |
| Launch of the focus groups (WP nr 3) | Alicia | 8 |  |
| Introduction to the tools designed for the FGs (WP nr2) : - Guidelines for conducting FGs - Grid of questions - Grid for the observation of non verbal language | Paola Vulterini | Tools: -Guideline for conducting a focus group -Grid for conducting focus groups -Questions grid Observation grid | *The grid should contain more questions. *Each point should include its objective and information to be collected. *Define the profile of the moderator. * Which kinds of skills of the person with DS, the professional should be able to detect, in order to design the pedagogical model? |
| The dissemination plan (WP nr 8) | Katalin Gruiz | 6 | *Google drive will be used for sharing documents. *The web site will be designed according to DRUPAL open source content management system. * Every partner will be responsible for the contents in its own language. *FCSD will translate some resources into Catalan. * All partners will send AIPD an estimate of the expenses for graphic and printing. |
| Next steps and next coordination meeting | Paola Vulterini | 5 | *Next meeting will take place in Budapest, on the 6th of June 2013. *Minutes of the meetings will be drafted by the hosting partner. This time AIPD took the responsibility of them. |
| SWOT analysis | Paola Vulterini and all the other partners | SWOT |  |

November ,17, am

| Topic | Speaker | Attach | Comments |
| --- | --- | --- | --- |
| Explanation of the budget | Maria Giulia Senni | 7 |  |
| Instructions for finance reporting | Maria Giulia Senni | 7 |  |
| The contract between The Commission and AIPD. Contracts with partners | Maria Giulia Senni |  |  |
| Monitoring and Evaluation procedures (WP nr 7) | Paola Vulterini | Evaluation and results |  |

Next steps as agreed in the first co-ordination meeting (Barcelona, 15-17 November 2012) List of the attachement

- AIPD will send this list to partners by the 20th of November 2012. (AIPD)

- Discuss and send  back the contract with aipd (FCSD, HUDF,IFI)

- Report of the first coordination meeting , 30 November 2012 (AIPD)

- Review the project and the budget in order to clarify everything (FCSD, HUDF,IFI)

- Receive the tools (as changed during the coordination meeting) for FG and Exchange e mails with the expert, Clio Marco Veronesi. (FCSD, HUDF,IFI)

- Starting selection of participants in the FGs (All)

- Finding premises for the FGs (HUDF)

- First financial report, by the end of January 2013 (to Maria Giulia Senni) (FCSD, HUDF,IFI)

- Prepare the web site and the dissemination plan. Katalin will send a `proposal Drupal+ sharing of documents (Google drive ). Web site must be published by 18 January 2013 (HUDF)

- Facebook page must be ready by 18 January 2013 (HUDF)

- Preparation of the next meeting (programme, hotel, venue, visit to the Foundation) (HUDF)

- Evaluation plan by the 29th of March 2013 (AIPD)

- Dissemination plan  by the 30th of November (AIPD will send Katalin the translation of the relevant wp contained in the Project) (AIPD + HUDF)

- Send  AIPD an estimate of the expenses for graphic and printing. (FCSD, HUDF,IFI)

List of the attachement

- Presentacciòn FCSD angles

- PPT AIPD

- PPT Presentacciòn IFI

- AIPD PPTDAHUGK

- pre progetto team building next steps_RIV

- Dissemination and website2

- FINANCIAL INFORMATION

- PPT - WP 3 Focus Groups IFI

See the “List of attachement” below