Next steps as agreed in the first co-ordination meeting (Barcelona, 15-17 November 2012) List of the attachement

- AIPD will send this list to partners by the 20th of November 2012 (AIPD)

- Discuss and send back the contract with aipd (FCSD, HUDF, IFI)

- Report of the first coordination meeting , 30 November 2012(AIPD)

- Review the project and the budget in order to clarify everything(FCSD, HUDF, IFI)

- Receive the tools (as changed during the coordination meeting) for FG and Exchange e mails with the expert, Clio Marco Veronesi. (FCSD, HUDF, IFI)

- Starting selection of participants in the FGs (All)

- Finding premises for the FGs (HUDF)

- First financial report, by the end of January 2013 (to Maria Giulia Senni) (FCSD, HUDF,IFI)

- Prepare the web site and the dissemination plan. Katalin will send a `proposal Drupal+ sharing of documents (Google drive ). Web site must be published by 18 January 2013 (HUDF)

- Facebook page must be ready by 18 January 2013 (HUDF)

- Preparation of the next meeting (programme, hotel, venue, visit to the Foundation) (HUDF)

- Evaluation plan by the 29th of March 2013 (AIPD)

- Dissemination plan by the 30th of November (AIPD will send Katalin the translation of the relevant wp contained in the Project) (AIPD + HUDF)

- Send AIPD an estimate of the expenses for graphic and printing. (FCSD, HUDF, IFI)

List of the attachement

- Presentacciòn FCSD angles

- PPT AIPD

- PPT Presentacciòn IFI

- AIPD PPTDAHUGK

- pre progetto team building next steps_RIV

- Dissemination and website2

- FINANCIAL INFORMATION

- PPT - WP 3 Focus Groups IFI